## Instructions
Stakeholder analysis instructions
You can modify the spreadsheets for your own use
Please delete existing pre-populated data or diagrams
A1: Create a list of stakeholders that could be involved in your scenario, identify the type of stakeholders involved and how they might influence the surveillance system
A2: Understand how your stakeholders might interact with each other by creating a matrix
A3: Analyse the stakeholders, understand how much interest/influence they have on your surveillance system
A4: Plan engagement with different stakeholders based on the findings of the analysis

## A1_Stakeholder ID - database
Stakeholder identification
|  |  | Project name: | Project title
Stakeholder | Internal/ External | Stakeholder type/group | Relevance & function | Advocate/ Neutral/ Blocker | Why A/N/B? | Barriers to participation
Questions
Who will be involved in the project?
Who will be affected by your project activities ? Both positively and negatively (e.g. who may suffer disadvantages, exposed to risks, adverse effects)
Who will be able to influence the outcomes of the project ?
Who are the potential supporters of ISTER and who would be opponents or disinterested ?
What partnerships might build around the issues involved ?
Whose voices or interest on the subject might not be heard ? Key opinion leaders
Who will be the end users
Who can facilitate or impede the outcomes through their participation or non-participation ?
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: External stakeholders are groups or individuals outside of your organization. Internal stakeholders are groups or individuals within your organization.
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: e.g. government/ministry/public/research/academia/funder/commercial/environmental
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How are they relevant to the project; What do they do e.g. shape policies etc…
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If blocker can you move them to A or N as required

## A2_Stakeholder matrix
Stakeholder matrix
|  | Project name: | Project name
| Stakeholder 1 | Stakeholder 2 | Stakeholder 3 | Stakeholder 4 | Stakeholder 5 | Stakeholder 6 | Stakeholder 7 | Stakeholder 8 | Stakeholder 9 | Stakeholder 10
Stakeholder 1
Stakeholder 2
Stakeholder 3
Stakeholder 4
Stakeholder 5
Stakeholder 6
Stakeholder 7
Stakeholder 8
Stakeholder 9
Stakeholder 10
What are the relationships between the stakeholder groups and individuals?
Two-way relationship collaboration
One-way relationship, information
No information
Linkages targeted for implementation

## A3_Stakeholder analysis
Stakeholder map
|  | Project name: | Project name
| Stakeholder Name | Power | Influence
#1 | Person 1 | 4 | 9
#2 | Person 2 | 4 | 6
#3 | Person 3 | 2 | 8
#4 | Person 4 | 9 | 9
#5 | Person 5
#6 | Person 6
#7 | Person 7
#8 | Person 8
#9 | Person 9
#10 | Person 10
#11 | Person 11
#12 | Person 12
#13 | Person 13
#14 | Person 14
#15 | Person 15
#16 | Person 16
#17 | Person 17
#18 | Person 18
#19 | Person 19
#20 | Person 20
| Chart | 5 | 5
1 | No
2 | Slightly
3 | Shallow
4 | Fairly
5 | Neutral
6 | Moderately
7 | Quite
8 | Very
9 | Strongly
10 | Extremely

## A4_Engagement plan
Stakeholder engagement
Project name
| Stakeholder 1 | Stakeholder 2 | Stakeholder 3 | Stakeholder 4 | Stakeholder 5 | Stakeholder 6
Purpose of engagement
What are the foreseen activities and their value to thstakeholders? Goals and interests, what will they gain form the project?
What information do they need?
How will you communicate/engage? Which methods or activities are emost suitable to for engagement?
Timing of engagement (once, repeatedly, at what stages of the project?)
Potential collaborations
Resources required for engagement
Methods of engagement
Questionnaires and Surveys | Structured way of obtaining basic information which can be easily analysed statistically. Able to reach a large number of people, they are convenient, economic and thus a good staring point. They need to be well structured and ensure that the questions are not leading.
Media | Engages large numbers of the population, through television, newspapers and radio. Useful at reaching those who may be more difficult to involve. Internet, websites, online questionnaires, chat rooms and notice boards have become increasingly popular ways of providing information and seeking feedback.
Public meetings | Able to reach large numbers of people if well-advertised. Allows face to face feedback of information. Public Meetings enable presentation of basic information to the general public. Allow large numbers of people to be involved in some limited discussion. Need to be carefully managed to ensure all views are heard. Cheaper than exhibitions and road shows.
Reports | Useful for keeping key stakeholders informed
Structured interviews or semi-structured interviews | Useful in exploring more complex issues from key stakeholders later in the SMP process. The more open questions together with some structure allow a compromise between a thorough exploration of the issues and ease of analysis of responses.
Focus group discussions | Involves small groups (6-12) of people, which are asked questions by an experienced facilitator. Allows facilitator to probe emerging issues. It is resource intensive and may be more appropriately used later in the process.
Workshop | Structured group discussions designed to solve problems and identify ways forward. Useful in bringing different groups of experts together and require experienced facilitators as well as careful explanation to the attendees.
Roundtable discussions | Facilitated debates between groups with different views with the aim of reaching consensus. Useful for engaging specialist interest and single-issue groups.
Source: Appendix A4: Stakeholder Engagement Strategy (https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/69208/smpg-vol2-appa.pdf)